## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count | Type
1 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Identify funding to reinstate the Active Your Space program. *Active Your Space funds neighborhood projects that focus on crime prevention through environmental designs i.e. reworking outdoor spaces to disrupt drug activity | ECB | Complete | 1 | Action
2 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Organize regular (either bi-weekly or monthly) Community Engagement Walks in neighborhoods with high levels of murders and shootings. | MON | Complete | 1 | Action
3 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Organize quarterly town halls to allow communities to learn directly about the violence prevention plan and how it is working in their community | MON | In Progress | 1 | Action
4 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Implement and evaluate the group violence reduction strategy | MONSE | Not Yet Started | 1 | Action
5 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Expand Investment in Community Violence Intervention programs such as Safe Streets & hospital-based interrupters | MONSE | Complete | 1 | Action
6 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Expand and strengthen victim services and advocacy for victims of shootings, inter-personal violence, sexual violence, child abuse, and human trafficking | MONSE | In Progress | 1 | Action
7 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Continue to operate a regular PoliceStat process focused on using data to track, analyze, and improve the effectiveness of the Baltimore Police Department’s core violence reduction strategies. | OPI | In Progress | 1 | Action
8 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Review impact of GVRS pilot and potential for expansion | BPD | In Progress | 1 | Action
9 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Stand up a dedicated unit to support the investigative, enforcement and outreach functions for GVRS | BPD | Not Yet Started | 1 | Action
10 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Continue weekly shooting review meetings in the Western District as part of the GVRS Pilot | BPD | In Progress | 1 | Action
11 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Develop a specialized curriculum to ensure all officers assigned to the GVRS unit develop skill in investigations, tactics, procedural justice, partnerships, respectful engagement | BPD | Not Yet Started | 1 | Action
12 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Number of homicides (FY) |  | Complete | 1 | KPI
13 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | [Resident public safety perception survey metric?] Percentage of survey respondents percieving violent crime as getting worse |  | Complete | 1 | KPI
14 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Number of shootings |  | In Progress | 1 | KPI
15 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Number of partner CBOs |  | Not Yet Started | 1 | KPI
16 | Reach full implementation and compliance with the consent decree. | Demonstrate sustained compliance on a minimum of (4) four sections of the Consent Decree subject areas | Law | Complete | 1 | Action
17 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Develop and operationalize improved data tools that will allow City agencies and other partners to track the origin of illegal guns and to enable improved responses from city government and partners | OPI | In Progress | 1 | Action
18 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Establish the Firearms Intelligence Unit along with a multi-year gun trafficking investigation strategy | BPD | In Progress | 1 | Action
19 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Expand the Crime Gun Intelligence Center to pilot an additional police district | BPD | In Progress | 1 | Action
20 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Number of violent crimes committed with illegal guns |  |  |  | KPI
21 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Clearance rate for violent crime cases comitted with illegal guns |  |  |  | KPI
22 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Number of cases with illegal guns taken up by Federal |  |  |  | KPI
23 | Increase support for returning residents, particularly around treatment, family strengthening, and employment services. | Launch a local Re-entry Action Network of city agencies and community organizations to ensure seamless service | MONSE |  |  | Action
24 | Increase support for returning residents, particularly around treatment, family strengthening, and employment services. | Develop safe return plans for returning residents in coordination with DPSCS | MONSE |  |  | Action
25 | Increase support for returning residents, particularly around treatment, family strengthening, and employment services. | Reduce Barriers to City Government Employment | MONSE |  |  | Action
26 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Identify community sites to serve as coordinated entry points to assist and refer households at-risk or experiencing homelessness. | MOHS |  |  | Action
27 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Train BPD sworn personnel in crisis response and new behavioral health policies | Law |  |  | Action
28 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Diversion of behavioral health calls: Will identify additional ProQA determinants eligible for diversion to a 24/7 behavioral health line. Will develop information / data collection systems necessary for 911 and Fire Communications to have complete ownership of program administration. Improved data collection will result in publication of public-facing and internal dashboards. | Fire |  |  | Action
29 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Complete the Outreach Encampment Resource Guide and establish connections to medical/mental/behavioral health resources | MOHS |  |  | Action
30 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Number of diverted CFS |  |  |  | KPI
31 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Percent of CFS diverted |  |  |  | KPI
32 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Number of CFS diverted for co-response (vs. exclusively external parter) |  |  |  | KPI
33 | Establish a multi-year strategic plan to modernize the City’s Emergency Medical Services. | Percent of EMS responses within 9 minutes |  |  |  | KPI
34 | Establish a multi-year strategic plan to modernize the City’s Emergency Medical Services. | Number of alternative transports |  |  |  | KPI
35 | Establish a multi-year strategic plan to modernize the City’s Emergency Medical Services. | Calls resolved requiring no transport |  |  |  | KPI
36 | Modernize the City’s Emergency Medical System. | Expand the EMS Division to include additional executive management and top management positions and its infrastructure to create the appropriate staffing model to fulfill the needs of the department and to best serve the community | Fire |  |  | Action
37 | Modernize the City’s Emergency Medical System. | Identify new revenue sources while enhancing existing ambulance billing revenue to develop a sound financial base for acquiring and maintaining resources necessary to operate a comprehensive, reliable and safe EMS system | Fire |  |  | Action
38 | Strengthen federal, state, and regional coordination on joint efforts focused on prevention, intervention, enforcement, and re-entry. | Establish a Shooting Response Protocol within a Coordinated Neighborhood Stabilization Response (CNSR) to decrease retaliation, address trauma, and promote healing | MONSE |  |  | Action
39 | Strengthen federal, state, and regional coordination on joint efforts focused on prevention, intervention, enforcement, and re-entry. | Number of cases Federally prosecuted |  |  |  | KPI
40 | Strengthen federal, state, and regional coordination on joint efforts focused on prevention, intervention, enforcement, and re-entry. | Number of products developed by CJCC |  |  |  | KPI
41 | Strengthen federal, state, and regional coordination on joint efforts focused on prevention, intervention, enforcement, and re-entry. | Total grant dollars CIty receives for prevention programs |  |  |  | KPI
Note on A1: Im comfortable with changing this, but let me know if you want me to hold for approval. -Markele Cullins ---- Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
2 | 2020-12-09 | 2020-12-09
3 | 2020-12-10 | 2020-12-10
4 | 2020-12-11 | 2020-12-11
5 | 2020-12-12 | 2020-12-12
6 | 2020-12-13 | 2020-12-13
7 | 2020-12-14 | 2020-12-14
8 | 2020-12-15 | 2020-12-15
9 | 2020-12-16 | 2020-12-16
10 | 2020-12-17 | 2020-12-17
11 | 2020-12-18 | 2020-12-18
12 | 2020-12-19 | 2020-12-19
13 | 2020-12-20 | 2020-12-20
14 | 2020-12-21 | 2020-12-21
15 | 2020-12-22 | 2020-12-22
16 | 2020-12-23 | 2020-12-23
17 | 2020-12-24 | 2020-12-24
18 | 2020-12-25 | 2020-12-25
19 | 2020-12-26 | 2020-12-26
20 | 2020-12-27 | 2020-12-27
21 | 2020-12-28 | 2020-12-28
22 | 2020-12-29 | 2020-12-29
23 | 2020-12-30 | 2020-12-30
24 | 2020-12-31 | 2020-12-31
25 | 2021-01-01 | 2021-01-01 | First quarter ends
26 | 2021-01-02 | 2021-01-02
27 | 2021-01-03 | 2021-01-03
28 | 2021-01-04 | 2021-01-04
29 | 2021-01-05 | 2021-01-05
30 | 2021-01-06 | 2021-01-06
31 | 2021-01-07 | 2021-01-07
32 | 2021-01-08 | 2021-01-08
33 | 2021-01-09 | 2021-01-09
34 | 2021-01-10 | 2021-01-10
35 | 2021-01-11 | 2021-01-11
36 | 2021-01-12 | 2021-01-12
37 | 2021-01-13 | 2021-01-13
38 | 2021-01-14 | 2021-01-14
39 | 2021-01-15 | 2021-01-15
40 | 2021-01-16 | 2021-01-16
41 | 2021-01-17 | 2021-01-17
42 | 2021-01-18 | 2021-01-18
43 | 2021-01-19 | 2021-01-19
44 | 2021-01-20 | 2021-01-20
45 | 2021-01-21 | 2021-01-21
46 | 2021-01-22 | 2021-01-22
47 | 2021-01-23 | 2021-01-23
48 | 2021-01-24 | 2021-01-24
49 | 2021-01-25 | 2021-01-25
50 | 2021-01-26 | 2021-01-26 | First half ends
51 | 2021-01-27 | 2021-01-27
52 | 2021-01-28 | 2021-01-28
53 | 2021-01-29 | 2021-01-29
54 | 2021-01-30 | 2021-01-30
55 | 2021-01-31 | 2021-01-31
56 | 2021-02-01 | 2021-02-01
57 | 2021-02-02 | 2021-02-02
58 | 2021-02-03 | 2021-02-03
59 | 2021-02-04 | 2021-02-04
60 | 2021-02-05 | 2021-02-05
61 | 2021-02-06 | 2021-02-06
62 | 2021-02-07 | 2021-02-07
63 | 2021-02-08 | 2021-02-08
64 | 2021-02-09 | 2021-02-09
65 | 2021-02-10 | 2021-02-10
66 | 2021-02-11 | 2021-02-11
67 | 2021-02-12 | 2021-02-12
68 | 2021-02-13 | 2021-02-13
69 | 2021-02-14 | 2021-02-14
70 | 2021-02-15 | 2021-02-15
71 | 2021-02-16 | 2021-02-16
72 | 2021-02-17 | 2021-02-17
73 | 2021-02-18 | 2021-02-18
74 | 2021-02-19 | 2021-02-19
75 | 2021-02-20 | 2021-02-20 | Third quarter ends
76 | 2021-02-21 | 2021-02-21
77 | 2021-02-22 | 2021-02-22
78 | 2021-02-23 | 2021-02-23
79 | 2021-02-24 | 2021-02-24
80 | 2021-02-25 | 2021-02-25
81 | 2021-02-26 | 2021-02-26
82 | 2021-02-27 | 2021-02-27
83 | 2021-02-28 | 2021-02-28
84 | 2021-03-01 | 2021-03-01
85 | 2021-03-02 | 2021-03-02
86 | 2021-03-03 | 2021-03-03
87 | 2021-03-04 | 2021-03-04
88 | 2021-03-05 | 2021-03-05
89 | 2021-03-06 | 2021-03-06
90 | 2021-03-07 | 2021-03-07
91 | 2021-03-08 | 2021-03-08
92 | 2021-03-09 | 2021-03-09
93 | 2021-03-10 | 2021-03-10
94 | 2021-03-11 | 2021-03-11
95 | 2021-03-12 | 2021-03-12
96 | 2021-03-13 | 2021-03-13
97 | 2021-03-14 | 2021-03-14
98 | 2021-03-15 | 2021-03-15
99 | 2021-03-16 | 2021-03-16
100 | 2021-03-17 | 2021-03-17 | End of first 100 days
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority
1 | Reduce murders and shootings, and achieve sustainable reductions in violence through an all-hands-on-deck approach in partnership with our communities. | Test
2 | Reach full implementation and compliance with the consent decree. | Commit to Equity at the Core of City Services
3 | Decrease the flow of illegal guns into Baltimore and hold gun traffickers accountable. | Expanding Opportunities for All of Baltimore's Youth
4 | Increase support for returning residents, particularly around treatment, family strengthening, and employment services. | Establishing Government Accountability from the Top Down
5 | Accelerate and expand efforts to divert appropriate emergency calls to trained behavioral health specialists and 9-1-1 alternative responses, making Baltimore a national leader. | Leading an Effective Coronavirus Response for All
Establish a multi-year strategic plan to modernize the City’s Emergency Medical Services.
Modernize the City’s Emergency Medical System.
Strengthen federal, state, and regional coordination on joint efforts focused on prevention, intervention, enforcement, and re-entry.

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/
Note on C20: This may change during the period the tracker is live. -Natalie Schultz-Henry