## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count | Type
1 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Stand-up Right to Counsel | DHCD | Complete | 1 | Action
2 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Implement Tax Sale Exemption Program | DHCD | Complete | 1 | Action
3 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Execute DHCD's Emergency Mortgage and Housing Program, the foreclosure assistance program for Baltimore City homeowners at risk of COVID-related foreclosure | DHCD | In Progress | 1 | Action
4 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Implement and monitor Security Deposit Program | DHCD | Not Yet Started | 1 | Action
5 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Fund Middle Neighborhoods program | DHCD | Complete | 1 | Action
6 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | ARP applications submitted for projects for improving equitable recovery for residents and businesses. Water Equity tool to be developed (one of 10 utilities participating) | DPW | In Progress | 1 | Action
7 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Ensure American Rescue Act dollars prioritize returning citizens, residents receiving public assistance and opportunity youth. Provide services to over 2,000 residents with these funds. | MOED | In Progress | 1 | Action
8 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Increase access to workforce services to neighborhoods that have traditionally not received investment. Establish at least 3 new Community Job Hubs. Provide services to at least 1500 residents through MOED Community Job Hubs. | MOED | In Progress | 1 | Action
9 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Increase resident wages at placement by an average of 5% each year. | MOED | Not Yet Started | 1 | Action
10 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Evaluate all agency proposals for ARPA funding to ensure a focus on equity; suggest ways for agencies to increase their equity focus in ARPA related proposals | MORP | In Progress | 1 | Action
11 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Conduct a survey of Baltimore City Businesses to Identify their short term and long term needs to re-open and sustain their businesses in community | MWOBD | Not Yet Started | 1 | Action
12 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Provide Microloans to small business | MWOBD | Complete | 1 | Action
13 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Measure agency performance of ARPA funded projects and initiatives through data to ensure equitable recovery; suggest changes to agency approach where equity goals are not on track | MORP | Complete | 1 | Action
14 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Provide Grants and other financial support to Baltimore City Small and minority Businesses. | MWOBD | In Progress | 1 | Action
15 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Fund implementation of the middle neighborhoods strategy with ARPA funds (see goal 4). | Planning | Not Yet Started | 1 | Action
16 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Unemployment |  | Complete | 1 | KPI
17 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Number of shuttered businesses |  | In Progress | 1 | KPI
18 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Vaccination rate |  | In Progress | 1 | KPI
19 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Spend down of ARPA, infrastructure bill funds |  | In Progress | 1 | KPI
20 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Update inclusionary housing ordinance to increase production of affordable housing in all neighborhoods | DHCD |  |  | Action
21 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Ensure CCG Capital grants are awarded in formerly redlined neighborhoods | DHCD |  |  | Action
22 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Identify and stabilize vacant structures with roof damage on blocks with 70%+ occupancy to prevent additional vacancy, stabilze the block and attract new homeowners | DHCD |  |  | Action
23 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Convene CDC learning network for the following sessions: p2p learning, establish leadership pipeline, foster development partnerships, share grant opporunities | DHCD |  |  | Action
24 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Continue to close all DHCD 311 requests within 4 business days | DHCD |  |  | Action
25 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | continued sustainability of supports for low and middle income seniors and legacy homeowners, HUBS is partner in this work, this will require expanded funding to serve the full population | DHCD |  |  | Action
26 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Fund Middle Neighborhoods proposal | DHCD |  |  | Action
27 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Fund IIAs proposal in order to execute block level strategies identified via IIA working groups | DHCD |  |  | Action
28 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Fund PSO infrastructure request to realize whole neighborhood transformation, build 21st Century school, create true mixed income community with 1:1 replacement of existing subsidized housing | DHCD |  |  | Action
29 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Fund Healthy Homes ARPA proposal | DHCD |  |  | Action
30 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Fund infrastructure requests for major affordable housing/new construction projects | DHCD |  |  | Action
31 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | All service brochures/invites/flyers will be translated into five most commonly spoken languages in Baltimore | DHCD |  |  | Action
32 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Complete process improvement evaluation for disposition of city-owned properties and implement recomendations with emphasis on reducing length of time for property disposition | DHCD |  |  | Action
33 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Address all transportation related service requests/ backlog through an equity lens. | DOT |  |  | Action
34 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Implement recommendations from the Equity Gap Analysis Study | DOT |  |  | Action
35 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Create a loan loss reserve fund to provide access to capital for minority and small businesses. | MWOBD |  |  | Action
36 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Develop and implement Neighborhood Policing Plans in two historically redlined communities | BPD |  |  | Action
37 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Complete the Pennrose PILOT Agreement for a new market rate apartment project at EBDI. | BDC |  |  | Action
38 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Seek master plan and zoning approval for a new Pimlico redevelopment. | BDC |  |  | Action
39 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Create a line of credit facility for Baltimore City vendors. | MWOBD |  |  | Action
40 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Total number of vacant buildings |  |  |  | KPI
41 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Total capital + ARPA +infrastructure spending in redlined neighborhoods |  |  |  | KPI
42 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Create opportunities for minority and women-owned small businesses to bid on a portion of the Mowing/ Landscaping contract for BCRP. Small businesses can manage the maintenance of abandoned and blighted properties. | BCRP |  |  | Action
43 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Increase funding/accessibility for facade grants | DHCD |  |  | Action
44 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | BCRP will identify CIP project opportunities in every park located in a formerly redlined neighborhood. | BCRP |  |  | Action
45 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | BCRP will modify their current CIP project scoring matrix to include additional priority points for parks located in formerly redlined neighborhoods. | BCRP |  |  | Action
46 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Create workforce development program related to blight removal | DHCD |  |  | Action
47 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Proactively address all transportation-related service request within commercial corridors to ensure pedestrian safety and mobility. | DOT |  |  | Action
48 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Establish a financial incentive for small, minority-owned businesses to hire city residents whose employment has been impacted by the pandemic. Invest at least $1 million in a wage subsidy for small, minority-owned businesses that create at least 150 jobs. | MOED |  |  | Action
49 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Open a new Lexington Market. | BDC |  |  | Action
50 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Complete a major renovation of the Baltimore Arena. | BDC |  |  | Action
51 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Launch a new loan loss reserve fund to support capital lending to BIPOC-owned businesses. | BDC |  |  | Action
52 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Evaluate economic development related proposals for ARPA funding to support this goal. | MORP |  |  | Action
53 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Develop an Economic Recovery Fund to assist local, small, women-owned and Black-and Brown-owned businesses with economic recovery from the COVID-19 pandemic | MORP |  |  | Action
54 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Support all Main Street managers with additional funding to increase their capacity to develop their work in 8 main streets. | MWOBD |  |  | Action
55 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Increase funding for facade grants in Commercial corridors (Arts districts, BID, RBDL and Mainstreets) | MWOBD |  |  | Action
56 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | MWBD is the recipient of a Advance Manufacturing Grant from MBDA to assist minority owned businesses with the development of prototypes and manufacturing business development | MWOBD |  |  | Action
57 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | % participation/$ of MBE/WBE in Baltimore city contracts |  |  |  | KPI
58 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Number of MBE/WBEs and/or revenue? |  |  |  | KPI
59 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | % increase of hotel tax collected as it correlates to tourism non-local visitors to Baltimore |  |  |  | KPI
60 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Implement Middle Neighborhoods Strategy in areas through following actions: lead proces to select MN priorirty areas, award grants for neighborhood organizations, administer home repair grants | DHCD |  |  | Action
61 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Analyze impact of existing homebuying incentives and re-evaluate program requirements and parameters to meet the needs of target populations | DHCD |  |  | Action
62 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Collaboration with MONSE and BPD to implement Mayor's Violence Prevention Plan | DHCD |  |  | Action
63 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Analyze and assess property tax credits currently on the books through the lens of equity | DHCD |  |  | Action
64 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Analyze and assess property tax credits currently on the books through the lens of equity | DHCD |  |  | Action
65 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | DOP, DHCD, BBMR establish a total, financially feasible tax credit pool that can be split among any number of City's tax abatement programs. | DHCD |  |  | Action
66 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Work with lending institutions to increase access to mortgages for properties priced below $80,000 | DHCD |  |  | Action
67 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Create and deploy outreach strategy to increase usage of Homeowner and Homestead Tax Credits | DHCD |  |  | Action
68 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Evaluate workforce development and housing-related proposals for ARPA funding to ensure that proposals address the target population (middle income families). | MORP |  |  | Action
69 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Through consultants and university partnerships, research and provide information and data on best practices for workforce development and housing that address the target population | MWOBD |  |  | Action
70 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Make financial and operating resources available to entrepreneurs who might look to open businesses in communities where they live. | BCIT |  |  | Action
71 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Baltimore population estimate |  |  |  | KPI
72 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Middle income population estimate |  |  |  | KPI
73 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Immigrant population estimate |  |  |  | KPI
74 | Close the digital divide once and for all. | Increasing Minority & Women-Owned Enterprises Participation with BCIT Professional Service Needs | BCIT |  |  | Action
75 | Close the digital divide once and for all. | All BCRP recreation centers will have technology available for public use. | BCRP |  |  | Action
76 | Close the digital divide once and for all. | BCRP will provide STEAM programming and/or technology training at recreation centers in each district | MOBDE |  |  | Action
77 | Close the digital divide once and for all. | Deploy citywide network of public wi-fi zones | MOBDE |  |  | Action
78 | Close the digital divide once and for all. | Computing device giveaways in public housing developments | MOBDE |  |  | Action
79 | Close the digital divide once and for all. | Require new infrastructure project plans to incorporate broadband accessibility as part of building design and budget | DHCD |  |  | Action
80 | Close the digital divide once and for all. | NOFA language: include language on City's goals for infrastructure + WIFI for any DHCD EOIs, RFPs, etc. | DHCD |  |  | Action
81 | Close the digital divide once and for all. | Align PEG capital funding with broadband initiatives | DHCD |  |  | Action
82 | Close the digital divide once and for all. | Administer subrecipient grants using CDBG allocation for organizations that provide internet access/infrastructure to assist in closing the digital divide | DHCD |  |  | Action
83 | Close the digital divide once and for all. | Partner with HABC to ensure broadband access in existing housing and RAD conversions | Planning |  |  | Action
84 | Close the digital divide once and for all. | Evaluate proposals for ARPA funding related to broadband access for efficacy, efficiency and equity | MORP |  |  | Action
85 | Close the digital divide once and for all. | Assist with coordinating agency partners on digital divide related proposals for ARPA funding to minimize duplication and increase efficiency | MWOBD |  |  | Action
86 | Close the digital divide once and for all. | Continue to expand wi-fi access via our branch locations, hotspots, wifi enabled devices with additional support by librarian professionals, social workers, etc. | Pratt Library |  |  | Action
87 | Close the digital divide once and for all. | Establish technology support and training for residents with a need to ensure successful adoption of technology and integration into their live | Pratt Library |  |  | Action
Note on A1: Im comfortable with changing this, but let me know if you want me to hold for approval. -Markele Cullins ---- Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
2 | 2020-12-09 | 2020-12-09
3 | 2020-12-10 | 2020-12-10
4 | 2020-12-11 | 2020-12-11
5 | 2020-12-12 | 2020-12-12
6 | 2020-12-13 | 2020-12-13
7 | 2020-12-14 | 2020-12-14
8 | 2020-12-15 | 2020-12-15
9 | 2020-12-16 | 2020-12-16
10 | 2020-12-17 | 2020-12-17
11 | 2020-12-18 | 2020-12-18
12 | 2020-12-19 | 2020-12-19
13 | 2020-12-20 | 2020-12-20
14 | 2020-12-21 | 2020-12-21
15 | 2020-12-22 | 2020-12-22
16 | 2020-12-23 | 2020-12-23
17 | 2020-12-24 | 2020-12-24
18 | 2020-12-25 | 2020-12-25
19 | 2020-12-26 | 2020-12-26
20 | 2020-12-27 | 2020-12-27
21 | 2020-12-28 | 2020-12-28
22 | 2020-12-29 | 2020-12-29
23 | 2020-12-30 | 2020-12-30
24 | 2020-12-31 | 2020-12-31
25 | 2021-01-01 | 2021-01-01 | First quarter ends
26 | 2021-01-02 | 2021-01-02
27 | 2021-01-03 | 2021-01-03
28 | 2021-01-04 | 2021-01-04
29 | 2021-01-05 | 2021-01-05
30 | 2021-01-06 | 2021-01-06
31 | 2021-01-07 | 2021-01-07
32 | 2021-01-08 | 2021-01-08
33 | 2021-01-09 | 2021-01-09
34 | 2021-01-10 | 2021-01-10
35 | 2021-01-11 | 2021-01-11
36 | 2021-01-12 | 2021-01-12
37 | 2021-01-13 | 2021-01-13
38 | 2021-01-14 | 2021-01-14
39 | 2021-01-15 | 2021-01-15
40 | 2021-01-16 | 2021-01-16
41 | 2021-01-17 | 2021-01-17
42 | 2021-01-18 | 2021-01-18
43 | 2021-01-19 | 2021-01-19
44 | 2021-01-20 | 2021-01-20
45 | 2021-01-21 | 2021-01-21
46 | 2021-01-22 | 2021-01-22
47 | 2021-01-23 | 2021-01-23
48 | 2021-01-24 | 2021-01-24
49 | 2021-01-25 | 2021-01-25
50 | 2021-01-26 | 2021-01-26 | First half ends
51 | 2021-01-27 | 2021-01-27
52 | 2021-01-28 | 2021-01-28
53 | 2021-01-29 | 2021-01-29
54 | 2021-01-30 | 2021-01-30
55 | 2021-01-31 | 2021-01-31
56 | 2021-02-01 | 2021-02-01
57 | 2021-02-02 | 2021-02-02
58 | 2021-02-03 | 2021-02-03
59 | 2021-02-04 | 2021-02-04
60 | 2021-02-05 | 2021-02-05
61 | 2021-02-06 | 2021-02-06
62 | 2021-02-07 | 2021-02-07
63 | 2021-02-08 | 2021-02-08
64 | 2021-02-09 | 2021-02-09
65 | 2021-02-10 | 2021-02-10
66 | 2021-02-11 | 2021-02-11
67 | 2021-02-12 | 2021-02-12
68 | 2021-02-13 | 2021-02-13
69 | 2021-02-14 | 2021-02-14
70 | 2021-02-15 | 2021-02-15
71 | 2021-02-16 | 2021-02-16
72 | 2021-02-17 | 2021-02-17
73 | 2021-02-18 | 2021-02-18
74 | 2021-02-19 | 2021-02-19
75 | 2021-02-20 | 2021-02-20 | Third quarter ends
76 | 2021-02-21 | 2021-02-21
77 | 2021-02-22 | 2021-02-22
78 | 2021-02-23 | 2021-02-23
79 | 2021-02-24 | 2021-02-24
80 | 2021-02-25 | 2021-02-25
81 | 2021-02-26 | 2021-02-26
82 | 2021-02-27 | 2021-02-27
83 | 2021-02-28 | 2021-02-28
84 | 2021-03-01 | 2021-03-01
85 | 2021-03-02 | 2021-03-02
86 | 2021-03-03 | 2021-03-03
87 | 2021-03-04 | 2021-03-04
88 | 2021-03-05 | 2021-03-05
89 | 2021-03-06 | 2021-03-06
90 | 2021-03-07 | 2021-03-07
91 | 2021-03-08 | 2021-03-08
92 | 2021-03-09 | 2021-03-09
93 | 2021-03-10 | 2021-03-10
94 | 2021-03-11 | 2021-03-11
95 | 2021-03-12 | 2021-03-12
96 | 2021-03-13 | 2021-03-13
97 | 2021-03-14 | 2021-03-14
98 | 2021-03-15 | 2021-03-15
99 | 2021-03-16 | 2021-03-16
100 | 2021-03-17 | 2021-03-17 | End of first 100 days
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority
1 | Continue to ensure an equitable recovery from COVID-19 for Baltimore residents and businesses. | Test
2 | Increase capital investment and ensure equitable access to services in formerly redlined neighborhoods. | Commit to Equity at the Core of City Services
3 | Reimagine and support Baltimore’s economic engines, commercial corridors, anchor institutions, and arts and cultural community to increase opportunities for local, small, women-owned and Black- and Brown-owned businesses. | Expanding Opportunities for All of Baltimore's Youth
4 | Increase Baltimore’s overall population with a focus on middle income families and immigrants. | Establishing Government Accountability from the Top Down
5 | Close the digital divide once and for all. | Leading an Effective Coronavirus Response for All

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/
Note on C20: This may change during the period the tracker is live. -Natalie Schultz-Henry