## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count | Type
1 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | 1.1 Establish connections between systems to pull data in a more regular/systematic fashion to better inform basic reporting (e.g. Integrify and CitiBuy,); ID requirements to create automations that allow us to deliver regular, consistent reporting | DGS | Complete | 1 | Action
2 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | 1.6 Develop broader policy framework and SOPs for executing key transactions and activities in ERP systems. | DGS | Complete | 1 | Action
3 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | 2. Identify and recommend DEI trainings for procurement officers. | OECR | In Progress | 1 | Action
4 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | 3. Draft EO requiring contractors to disclose and affirm their commitment to DEI as part of the procurement process | OECR | Not Yet Started | 1 | Action
5 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | Implement a state of the art financial accounting system used by all city agencies for appropriation and expenditure management of all fund sources. | Finance | Complete | 1 | Action
6 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | a. Automate the signature workflow process to ensure collaboration and ensure a history of document approvals. b. Automating collections of water bills. c. Developing a change order tracking dashboard for officials to review and/or approve. | Law | In Progress | 1 | Action
7 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | Percent of invoices paid within 30 days |  | In Progress | 1 | KPI
8 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | Number of annual single audit findings |  | In Progress | 1 | KPI
9 | Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 2.1 Require all employees to attend annual customer service training provided by DHR. | DGS | Not Yet Started | 1 | Action
10 | Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 1. OECR-CEO will collaborate with BCIT to make City websites ADA compliant | OECR | In Progress | 1 | Action
11 | Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 1. Establish clear metrics and measurement tools to track the impact and effectiveness of the Diversity, equity and inclusion movements within City Agencies. | DHR | Not Yet Started | 1 | Action
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | a. Develop an app/website for the public to make accessibility requests. b. Develop a marketing and outreach strategy to encourage minority and women businesses to move to Baltimore. | Law | Complete | 1 | Action
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 1. Develop and launch a “NeighborhoodStat”, which will allow city government leaders to use data to better analyze and improve the delivery of city services and programs at the neighborhood level. | OPI | Complete | 1 | Action
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 2. Reintroduce a comprehensive biennial Baltimore resident survey to systematically gather resident perspectives on a range of issues connected to city government – including city service delivery. | OPI | In Progress | 1 | Action
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | 1. Distribute 50,000 reusable bags to low-income households. | Planning | Not Yet Started | 1 | Action
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | [Metric from resident survey?] |  | Complete | 1 | KPI
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | Number of escalation SRs |  | In Progress | 1 | KPI
| Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | Overall 311 service request percent on-time completion in historically redlined neighborhoods |  | In Progress | 1 | KPI
| Recruit, retain, and develop a diverse and high-achieving workforce. | Develop a robust citywide data training program | Chief Data Officer | In Progress | 1 | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 2. Establish Bmore WISE workforce development program focusing on construction and maintenance training and development. | DPW |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.1 Evaluation of salary ranges. Comparing private and public wages, benefits, and compensation packages. Determine if a new compensation strategy is required. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.2 Evaluate the need to reduce stringent min qualifications required for certain positions. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.3 Create formalized career paths for each employee and craft training needs around carrier path | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.4 Institute a progressive series of Supervisor, Manager and Leadership training programs. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.5 Create a program that allows employees to temporarily transfer to other internal divisions, or external agencies, to learn different skill sets to determine carrier trajectory. See DGS Bungee program. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.9b Partner with local educational institutions to offer scholarships to City employees. From an equity perspective the current system favors higher-compensated individuals. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.12 Create a Human Capital Recruitment Dashboard that tracks all new hires and captures origin of introduction to the hiring process and their ongoing LOS with the City. Would encourage ongoing analysis of hiring channels to measure relative performance/impact of that stream of recruitment. Would establish City benchmark employee satisfaction survey and share data on an annual basis via the dashboard-by Agency | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 3.13 Perform and publish the results of comparative agencywide and city wide compensation parity analysis as the basis for long term compensation strategy for target positions. | DGS |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | 1. Examine the current hiring process and ensure we are able to hire quality candidates while reducing our Time-to- Fill. 2. Create a Succession Plan that will continue to strengthen the City’s workforce and create a pipeline to fill critical vacant positions quickly | DHR |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | Establish internship program with local universities and organizations to create a talent pool for entry level professionals for budgeting and accounting opportunities. | Finance |  |  | Action
| Recruit, retain, and develop a diverse and high-achieving workforce. | Annual number of unique individuals who complete at least one training |  |  |  | KPI
| Recruit, retain, and develop a diverse and high-achieving workforce. | Annual retention / turnover rate |  |  |  | KPI
| Improve government performance, accountability, and cross-agency collaboration. | Standardize process for data sharing between agencies | Chief Data Officer |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | Adopt a series of data standards that ensure data interoperability and interpretability | Chief Data Officer |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 3. Upgrade outdated construction management software called CM-14 to a new, stronger, and more robust system called Unifier. | DPW |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 4.1. Create a Municipal Building Performance Standard for energy, with progressive targets over time by building type | DGS |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 4.2. Create municipal greenhouse gas and energy reduction goals consistent with the City’s Climate Action Plan Update | DGS |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 2. The OECR-CEO will produce an equity tool kit and equity assessment tool that can be utilized by all agencies. | OECR |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | Develop and support the management of a new Baltimore City government performance management system which will provide a standardized agency-by-agency process for planning performance priorities, setting targets, monitor service delivery, and review performance-based indicators linked to an overall citywide performance management framework. | OPI |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 1. Launch Sustainability and Resiliency Subcabinet. | Planning |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | 5. Include capital budget in update of 10 Year Financial Plan. | Planning |  |  | Action
| Improve government performance, accountability, and cross-agency collaboration. | Overall 311 service request on-time performance |  |  |  | KPI
| Improve government performance, accountability, and cross-agency collaboration. | Proper transfer between agencies - on-time performance for transfered? |  |  |  | KPI
| Improve government performance, accountability, and cross-agency collaboration. | Percent of workforce that participates in performance evaluation process |  |  |  | KPI
| Increase transparency and meaningful resident participation in government. | Create MPIA request intake and tracking system | Chief Data Officer |  |  | Action
| Increase transparency and meaningful resident participation in government. | Establish clear pipeline for civic tech open source contributions | Chief Data Officer |  |  | Action
| Increase transparency and meaningful resident participation in government. | Expand Open Baltimore to include community-developed data tools and maps | Chief Data Officer |  |  | Action
| Increase transparency and meaningful resident participation in government. | Various Maps and reports available for public like water main breaks, OEC construction projects, MCD quarterly reports, that increase transparency and outreach. Also annual public forum for MCD. | DPW |  |  | Action
| Increase transparency and meaningful resident participation in government. | Implement New Payment Processing System | BCIT |  |  | Action
| Increase transparency and meaningful resident participation in government. | Upgrade and Re-Architect Baltimore City’s Website | BCIT |  |  | Action
| Increase transparency and meaningful resident participation in government. | Upgrade Legacy Mainframe Tax/Property Systems | BCIT |  |  | Action
| Increase transparency and meaningful resident participation in government. | Implement Consolidated Construction Management System | BCIT |  |  | Action
| Increase transparency and meaningful resident participation in government. | 1. In our plan to be open and transparent we will seek out new community organizations to create a forum to educate City residents about the opportunities for employment with the City. | DHR |  |  | Action
| Increase transparency and meaningful resident participation in government. | Reintroduce a comprehensive biennial Baltimore resident survey to systematically gather resident perspectives on a range of issues connected to city government – including city service delivery. | OPI |  |  | Action
| Increase transparency and meaningful resident participation in government. | 1. With MO and BCRP, BOPA & DGS, establish Monuments Commission to examine divisive monuments and identify actions. | Planning |  |  | Action
| Increase transparency and meaningful resident participation in government. | Number of visits to Open Baltimore |  |  |  | KPI
| Increase transparency and meaningful resident participation in government. | Number of individuals engaged in annual budget process |  |  |  | KPI
| Increase transparency and meaningful resident participation in government. | Number of government listserv subscribers |  |  |  | KPI
| Increase transparency and meaningful resident participation in government. | Number of unique individuals who submit at least one 311 service request |  |  |  | KPI
Note on A1: Im comfortable with changing this, but let me know if you want me to hold for approval. -Markele Cullins ---- Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
2 | 2020-12-09 | 2020-12-09
3 | 2020-12-10 | 2020-12-10
4 | 2020-12-11 | 2020-12-11
5 | 2020-12-12 | 2020-12-12
6 | 2020-12-13 | 2020-12-13
7 | 2020-12-14 | 2020-12-14
8 | 2020-12-15 | 2020-12-15
9 | 2020-12-16 | 2020-12-16
10 | 2020-12-17 | 2020-12-17
11 | 2020-12-18 | 2020-12-18
12 | 2020-12-19 | 2020-12-19
13 | 2020-12-20 | 2020-12-20
14 | 2020-12-21 | 2020-12-21
15 | 2020-12-22 | 2020-12-22
16 | 2020-12-23 | 2020-12-23
17 | 2020-12-24 | 2020-12-24
18 | 2020-12-25 | 2020-12-25
19 | 2020-12-26 | 2020-12-26
20 | 2020-12-27 | 2020-12-27
21 | 2020-12-28 | 2020-12-28
22 | 2020-12-29 | 2020-12-29
23 | 2020-12-30 | 2020-12-30
24 | 2020-12-31 | 2020-12-31
25 | 2021-01-01 | 2021-01-01 | First quarter ends
26 | 2021-01-02 | 2021-01-02
27 | 2021-01-03 | 2021-01-03
28 | 2021-01-04 | 2021-01-04
29 | 2021-01-05 | 2021-01-05
30 | 2021-01-06 | 2021-01-06
31 | 2021-01-07 | 2021-01-07
32 | 2021-01-08 | 2021-01-08
33 | 2021-01-09 | 2021-01-09
34 | 2021-01-10 | 2021-01-10
35 | 2021-01-11 | 2021-01-11
36 | 2021-01-12 | 2021-01-12
37 | 2021-01-13 | 2021-01-13
38 | 2021-01-14 | 2021-01-14
39 | 2021-01-15 | 2021-01-15
40 | 2021-01-16 | 2021-01-16
41 | 2021-01-17 | 2021-01-17
42 | 2021-01-18 | 2021-01-18
43 | 2021-01-19 | 2021-01-19
44 | 2021-01-20 | 2021-01-20
45 | 2021-01-21 | 2021-01-21
46 | 2021-01-22 | 2021-01-22
47 | 2021-01-23 | 2021-01-23
48 | 2021-01-24 | 2021-01-24
49 | 2021-01-25 | 2021-01-25
50 | 2021-01-26 | 2021-01-26 | First half ends
51 | 2021-01-27 | 2021-01-27
52 | 2021-01-28 | 2021-01-28
53 | 2021-01-29 | 2021-01-29
54 | 2021-01-30 | 2021-01-30
55 | 2021-01-31 | 2021-01-31
56 | 2021-02-01 | 2021-02-01
57 | 2021-02-02 | 2021-02-02
58 | 2021-02-03 | 2021-02-03
59 | 2021-02-04 | 2021-02-04
60 | 2021-02-05 | 2021-02-05
61 | 2021-02-06 | 2021-02-06
62 | 2021-02-07 | 2021-02-07
63 | 2021-02-08 | 2021-02-08
64 | 2021-02-09 | 2021-02-09
65 | 2021-02-10 | 2021-02-10
66 | 2021-02-11 | 2021-02-11
67 | 2021-02-12 | 2021-02-12
68 | 2021-02-13 | 2021-02-13
69 | 2021-02-14 | 2021-02-14
70 | 2021-02-15 | 2021-02-15
71 | 2021-02-16 | 2021-02-16
72 | 2021-02-17 | 2021-02-17
73 | 2021-02-18 | 2021-02-18
74 | 2021-02-19 | 2021-02-19
75 | 2021-02-20 | 2021-02-20 | Third quarter ends
76 | 2021-02-21 | 2021-02-21
77 | 2021-02-22 | 2021-02-22
78 | 2021-02-23 | 2021-02-23
79 | 2021-02-24 | 2021-02-24
80 | 2021-02-25 | 2021-02-25
81 | 2021-02-26 | 2021-02-26
82 | 2021-02-27 | 2021-02-27
83 | 2021-02-28 | 2021-02-28
84 | 2021-03-01 | 2021-03-01
85 | 2021-03-02 | 2021-03-02
86 | 2021-03-03 | 2021-03-03
87 | 2021-03-04 | 2021-03-04
88 | 2021-03-05 | 2021-03-05
89 | 2021-03-06 | 2021-03-06
90 | 2021-03-07 | 2021-03-07
91 | 2021-03-08 | 2021-03-08
92 | 2021-03-09 | 2021-03-09
93 | 2021-03-10 | 2021-03-10
94 | 2021-03-11 | 2021-03-11
95 | 2021-03-12 | 2021-03-12
96 | 2021-03-13 | 2021-03-13
97 | 2021-03-14 | 2021-03-14
98 | 2021-03-15 | 2021-03-15
99 | 2021-03-16 | 2021-03-16
100 | 2021-03-17 | 2021-03-17 | End of first 100 days
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority
1 | Improve overall reliability of the city's financial systems to provide access, transparency, and affordability | Test
2 | Deliver quality (and efficient) customer service to all residents through a lens of equity, accessibility, and accountability. | Commit to Equity at the Core of City Services
3 | Recruit, retain, and develop a diverse and high-achieving workforce. | Expanding Opportunities for All of Baltimore's Youth
4 | Improve government performance, accountability, and cross-agency collaboration. | Establishing Government Accountability from the Top Down
5 | Increase transparency and meaningful resident participation in government. | Leading an Effective Coronavirus Response for All

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/
Note on C20: This may change during the period the tracker is live. -Natalie Schultz-Henry