## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count | Type
1 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Continue lead hazard remediation program for households with children 6 years old or under present or visiting and/or pregnant women. | DHCD | Complete | 1 | Action
2 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Forestry will plant/provide 5,000 trees per year to city residents, targeting high priority neighborhoods. | BCRP | Complete | 1 | Action
3 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Train all city staff on how to administer naloxone. | BCHD | In Progress | 1 | Action
4 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Annual instances of lead poisoning in children 18 and under |  | Not Yet Started | 1 | KPI
5 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | City-funded substance abuse slots |  | Complete | 1 | KPI
6 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Asthma prevalance |  | In Progress | 1 | KPI
7 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Create a transit development plan that includes route changes, redevelopment, and expansion of current CCC routes. This includes working with the MTA on service planning from an equity lens. Spring 2022 for the proposal of routes and 2024 for potential implementation. | DOT | In Progress | 1 | Action
8 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Use the Project Prioritization Process in the Complete Streets Manual to help the development of DOT’s FY2023 Capital Improvement Program. | DOT | In Progress | 1 | Action
9 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Work with the Traffic Division and Bike Program to develop standards for traffic control setups in work zones that prioritize people with special needs, people walking and biking. | DOT | Not Yet Started | 1 | Action
10 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Continue COVID-19 Emergency Food Response operations and provide After Action Report. Increase online SNAP participation for residents by 50% | Planning | In Progress | 1 | Action
11 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Launch and expand nutrition incentives at healthy food retailers and farm vendors to improve the accessibility of healthy and affordable foods. | Planning | Not Yet Started | 1 | Action
12 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Collaborate with the MTA on a public engagement campaign to promote the sustainability benefits of transit and rebuild passenger trust in vehicle safety and sanitation. | Planning | Complete | 1 | Action
13 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Collaborate with community partners to add 4 new virtual supermarket sites | BCHD | Complete | 1 | Action
14 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Percent of city population living in food desert |  | In Progress | 1 | KPI
15 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Percent of city population that use public transportation to get to work |  | Not Yet Started | 1 | KPI
16 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Walk score |  | Complete | 1 | KPI
17 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | 1. Fully implement Water for All provisions. | DPW | In Progress | 1 | Action
18 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | 3. Negotiate with EPA and other stakeholders to develop plan for phase II consent decree inflow and infiltration projects | DPW | In Progress | 1 | Action
19 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | . 4. Complete Montebello filtration plant filter upgrades, electrical upgrades at the Patapsco and Back River wastewater treatment plants, the Biosolids Master Plan, and the Comprehensive Watershed Study. Also, begin Patapsco Wastewater Treatment Plant headworks project | DPW | In Progress | 1 | Action
20 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | 5. Implement Lead and Copper Rule LCR (LCR) | DPW |  |  | Action
21 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | Create internal Rules and Regulations that streamline the appeal process for DPW determinations under Article 24. | ECB |  |  | Action
22 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | Number of households enrolled in Water for All |  |  |  | KPI
23 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | Total dollar value of bill adjustments |  |  |  | KPI
24 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | 1. Distribute recycling carts to every household that receives City recycling service along with outreach. | DPW |  |  | Action
25 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | 5. Proceed with Food Matters Program to provide residential food scrap drop-off for composting, workshops on composting, outreach to institutions on food waste reduction and public outreach on food waste recycling. | DPW |  |  | Action
26 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | 6. Complete assessment of closed landfills to determine suitability for compost facility, recycling facility or transfer station. | DPW |  |  | Action
27 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Continue with holistic assessments and referrals/connections with wrap around services when engaging residents for home repair assistance. | DHCD |  |  | Action
28 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | 100% of trees under BCRP responsibility (street trees and developed parkland trees) will be recycled: 20k bf ft of lumber and 10k cu ft of mulch available for residents and city agencies (capital projects)/schools | BCRP |  |  | Action
29 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Work with the communities and Friends Groups to remove 100,000 or 45 tons of trash and debris from park property each year. | BCRP |  |  | Action
30 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Draft new climate change and resiliency criteria for evaluating capital budget requests. | Planning |  |  | Action
31 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Evaluate possible code improvements to increase building energy efficiency and/or resiliency. | Planning |  |  | Action
32 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Develop and fund new extreme heat mitigation/management strategies to create more equitable access to cooling opportunities. | Planning |  |  | Action
33 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Increase air quality monitoring in low-income neighborhoods. | Planning |  |  | Action
34 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Achieve Gold certification from US Green Building Council’s LEED for Cities. | Planning |  |  | Action
35 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Annual per capita recycling tonnage collected |  |  |  | KPI
36 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | 2. Increase transparency and accountability of on-line electronic plans submittal system as it relates to Storm Water Management. | DPW |  |  | Action
37 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | 4. Expand number of GROW Center Pop-up events | DPW |  |  | Action
38 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | 6. Implement a community volunteer clean-up program to support organizations, community groups and individuals who want to participate in clean-ups. | DPW |  |  | Action
39 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | 7. Resume mechanical street sweeping program. | DPW |  |  | Action
40 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | 10. Utilize routing software for entire Solid Waste fleet, making operations more efficient. | DPW |  |  | Action
41 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | Finalize and implement the new DOT traffic calming policy. (Dec 2021) | DOT |  |  | Action
42 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | Add 100 lots to the Care-A-Lot program Care-A-Lot provides funding for neighborhoods that care for and maintain City lots. Currently, There are over 1,000 lots under the program. | ECB |  |  | Action
43 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | Publish the “Framework to Recreate Vacant Lots.” Facilitate the creation of a program to hire local residents and contractors to maintain vacant lots as part of Phase II of Green Network Plan. This will require the following actions: Secure ARPA funds for this program. Inventory existing public, nonprofit and community programs with capacity to green and maintain vacant lots | Planning |  |  | Action
44 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | % of Greenway trails completed |  |  |  | KPI
45 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | % of city covered by urban canopy |  |  |  | KPI
46 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | Miles of bike lines |  |  |  | KPI
47 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Continue with the following programs and efforts: emergency mortgage and housing assistance, tax sale exemption program, and the Right to Counsel program. | DHCD |  |  | Action
48 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Re-structure emergency shelter capacity and access Demobilize prevention hotels established in response to COVID Implement winter shelter and code blue capacity and protocol Establish shelter capacity and develop process for shelter access incorporating process for outreach/first responders to access shelter beds Acquire hotel(s) for purchase to operate non-congregate shelter or to establish more permanent supportive housing Develop collaborative partnership to focus on high utilizers in Emergency Department and use year 2 of the ACIS program to support case management work | MOHS |  |  | Action
49 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Develop collaborative partnership to focus on high utilizers in Emergency Department and use year 2 of the ACIS program to support case management work | MOHS |  |  | Action
50 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Number of individuals experiencing long-term homelessness (point in time) |  |  |  | KPI
51 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Percent of homeless households who return to a homeless services program within 2 years of an exit to permanent housing |  |  |  | KPI
52 | Provide support services to reduce housing insecurity and homelessness in Baltimore. | Number of evictions prevented |  |  |  | KPI
Note on A1: Im comfortable with changing this, but let me know if you want me to hold for approval. -Markele Cullins ---- Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
2 | 2020-12-09 | 2020-12-09
3 | 2020-12-10 | 2020-12-10
4 | 2020-12-11 | 2020-12-11
5 | 2020-12-12 | 2020-12-12
6 | 2020-12-13 | 2020-12-13
7 | 2020-12-14 | 2020-12-14
8 | 2020-12-15 | 2020-12-15
9 | 2020-12-16 | 2020-12-16
10 | 2020-12-17 | 2020-12-17
11 | 2020-12-18 | 2020-12-18
12 | 2020-12-19 | 2020-12-19
13 | 2020-12-20 | 2020-12-20
14 | 2020-12-21 | 2020-12-21
15 | 2020-12-22 | 2020-12-22
16 | 2020-12-23 | 2020-12-23
17 | 2020-12-24 | 2020-12-24
18 | 2020-12-25 | 2020-12-25
19 | 2020-12-26 | 2020-12-26
20 | 2020-12-27 | 2020-12-27
21 | 2020-12-28 | 2020-12-28
22 | 2020-12-29 | 2020-12-29
23 | 2020-12-30 | 2020-12-30
24 | 2020-12-31 | 2020-12-31
25 | 2021-01-01 | 2021-01-01 | First quarter ends
26 | 2021-01-02 | 2021-01-02
27 | 2021-01-03 | 2021-01-03
28 | 2021-01-04 | 2021-01-04
29 | 2021-01-05 | 2021-01-05
30 | 2021-01-06 | 2021-01-06
31 | 2021-01-07 | 2021-01-07
32 | 2021-01-08 | 2021-01-08
33 | 2021-01-09 | 2021-01-09
34 | 2021-01-10 | 2021-01-10
35 | 2021-01-11 | 2021-01-11
36 | 2021-01-12 | 2021-01-12
37 | 2021-01-13 | 2021-01-13
38 | 2021-01-14 | 2021-01-14
39 | 2021-01-15 | 2021-01-15
40 | 2021-01-16 | 2021-01-16
41 | 2021-01-17 | 2021-01-17
42 | 2021-01-18 | 2021-01-18
43 | 2021-01-19 | 2021-01-19
44 | 2021-01-20 | 2021-01-20
45 | 2021-01-21 | 2021-01-21
46 | 2021-01-22 | 2021-01-22
47 | 2021-01-23 | 2021-01-23
48 | 2021-01-24 | 2021-01-24
49 | 2021-01-25 | 2021-01-25
50 | 2021-01-26 | 2021-01-26 | First half ends
51 | 2021-01-27 | 2021-01-27
52 | 2021-01-28 | 2021-01-28
53 | 2021-01-29 | 2021-01-29
54 | 2021-01-30 | 2021-01-30
55 | 2021-01-31 | 2021-01-31
56 | 2021-02-01 | 2021-02-01
57 | 2021-02-02 | 2021-02-02
58 | 2021-02-03 | 2021-02-03
59 | 2021-02-04 | 2021-02-04
60 | 2021-02-05 | 2021-02-05
61 | 2021-02-06 | 2021-02-06
62 | 2021-02-07 | 2021-02-07
63 | 2021-02-08 | 2021-02-08
64 | 2021-02-09 | 2021-02-09
65 | 2021-02-10 | 2021-02-10
66 | 2021-02-11 | 2021-02-11
67 | 2021-02-12 | 2021-02-12
68 | 2021-02-13 | 2021-02-13
69 | 2021-02-14 | 2021-02-14
70 | 2021-02-15 | 2021-02-15
71 | 2021-02-16 | 2021-02-16
72 | 2021-02-17 | 2021-02-17
73 | 2021-02-18 | 2021-02-18
74 | 2021-02-19 | 2021-02-19
75 | 2021-02-20 | 2021-02-20 | Third quarter ends
76 | 2021-02-21 | 2021-02-21
77 | 2021-02-22 | 2021-02-22
78 | 2021-02-23 | 2021-02-23
79 | 2021-02-24 | 2021-02-24
80 | 2021-02-25 | 2021-02-25
81 | 2021-02-26 | 2021-02-26
82 | 2021-02-27 | 2021-02-27
83 | 2021-02-28 | 2021-02-28
84 | 2021-03-01 | 2021-03-01
85 | 2021-03-02 | 2021-03-02
86 | 2021-03-03 | 2021-03-03
87 | 2021-03-04 | 2021-03-04
88 | 2021-03-05 | 2021-03-05
89 | 2021-03-06 | 2021-03-06
90 | 2021-03-07 | 2021-03-07
91 | 2021-03-08 | 2021-03-08
92 | 2021-03-09 | 2021-03-09
93 | 2021-03-10 | 2021-03-10
94 | 2021-03-11 | 2021-03-11
95 | 2021-03-12 | 2021-03-12
96 | 2021-03-13 | 2021-03-13
97 | 2021-03-14 | 2021-03-14
98 | 2021-03-15 | 2021-03-15
99 | 2021-03-16 | 2021-03-16
100 | 2021-03-17 | 2021-03-17 | End of first 100 days
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority
1 | Reduce public health disparities across the City, by decreasing instances of lead paint poisoning and overdoses as well as improving the City’s response to substance abuse and behavioral health crises. | Test
2 | Ensure every neighborhood can access affordable healthy food, reliable public transportation options, and quality streets and sidewalks. | Commit to Equity at the Core of City Services
3 | Provide an affordable, world class water service while maintaining safe and high-quality water standards. | Expanding Opportunities for All of Baltimore's Youth
4 | Move the City and residents towards a more sustainable future, and zero waste through improved recycling, composting, waste management, and other sustainable practices. | Establishing Government Accountability from the Top Down
5 | Expand green space and sustainably improve the cleanliness and usability of Baltimore’s streets, parks, and public spaces. | Leading an Effective Coronavirus Response for All
Provide support services to reduce housing insecurity and homelessness in Baltimore.

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/
Note on C20: This may change during the period the tracker is live. -Natalie Schultz-Henry